## Start Here
Block Party Planner
A starter template from Block Party ATX - keep it weird.
This is just a template to get you started.
Copy it and make it your own. Add, delete, and rename anything - every block is different. Tip: in Google Sheets, use File > Make a copy (or File > Import to upload this file), then edit away.
What's in here
Task Tracker
Every to-do from the 3-month timeline, grouped by phase. Check it off, assign an owner, add notes.
Budget Tracker
Estimated vs. actual costs, who funded what, and a spot to log receipts. Totals calculate automatically.
Donations & Sponsors
Track every business/donor: what they're giving, pickup time, and whether you've sent a thank-you.
Checkboxes
The Done / Thank-you columns use a click-to-pick box (empty or checked). Prefer true clickable checkboxes? In Google Sheets, select the column and choose Insert > Checkbox.

## Task Tracker
Task Tracker
Template - edit, reorder, or delete anything. Tick 'Done' as you go and assign an owner.
Done | Timeframe | Phase | Task | Assignee | Notes
☐ | 3+ months out | Float the idea & build your crew | Poll the block informally (text thread, door knocks, NextDoor) to gauge interest.
☐ | 3+ months out | Float the idea & build your crew | Recruit 3-5 neighbors for a party-planning committee.
☐ | 3+ months out | Float the idea & build your crew | Pick a target date AND a rain/backup date (avoid holiday weekends & back-to-school).
☐ | 3+ months out | Float the idea & build your crew | Pick a lead organizer and a money person (who holds funds / Venmo).
☐ | 3+ months out | Float the idea & build your crew | Start this shared tracker for to-dos, owners, and deadlines.
☐ | 3+ months out | Float the idea & build your crew | Start sponsor/donation outreach early - the earlier you ask, the more say yes.
☐ | ~10 weeks out | Host a kickoff meeting | Walk the committee through this task list; have people claim action items.
☐ | ~10 weeks out | Host a kickoff meeting | Decide the kind of party: potluck, live entertainment, kid/family focus - or a mix.
☐ | ~10 weeks out | Host a kickoff meeting | Pick a theme.
☐ | ~10 weeks out | Host a kickoff meeting | Draft a rough budget so you know your fundraising goal.
☐ | ~10 weeks out | Host a kickoff meeting | Schedule ALL planning meetings now and put them on everyone's calendar.
☐ | 8-10 weeks out | Collect signatures & start the permit | Confirm your street qualifies (residential, <=25 mph, no intersection/transit/signal).
☐ | 8-10 weeks out | Collect signatures & start the permit | Collect support from at least 60% of households; notify 100% of the block.
☐ | 8-10 weeks out | Collect signatures & start the permit | Map your closure points and where adult monitors will stand at each end.
☐ | 8-10 weeks out | Collect signatures & start the permit | Start the City of Austin block-party application (file by 15 days out - don't wait).
☐ | 8-10 weeks out | Collect signatures & start the permit | Design the flyer and build the online invite with a donation link + volunteer sign-up.
☐ | 6-8 weeks out | Source donations & book entertainment | Email or visit local food & beverage spots with your donation ask.
☐ | 6-8 weeks out | Source donations & book entertainment | Ask a local printer to cover or discount flyer printing.
☐ | 6-8 weeks out | Source donations & book entertainment | Line up monetary donors: neighborhood association, nonprofits, generous neighbors.
☐ | 6-8 weeks out | Source donations & book entertainment | Book entertainment (band/DJ/troupe/face painter); confirm fees & arrival times in writing.
☐ | 6-8 weeks out | Source donations & book entertainment | Reserve rentals: tables, chairs, barriers, tent, yard games, port-a-potty.
☐ | ~4 weeks out (1 month) | Promote everywhere & open volunteer sign-ups | Post printed flyers around the neighborhood (parks, cafes, daycares, boards).
☐ | ~4 weeks out (1 month) | Promote everywhere & open volunteer sign-ups | Get the invite into the neighborhood association newsletter and any listservs.
☐ | ~4 weeks out (1 month) | Promote everywhere & open volunteer sign-ups | Post on neighborhood social media and NextDoor.
☐ | ~4 weeks out (1 month) | Promote everywhere & open volunteer sign-ups | Open the volunteer sign-up and link it inside the online invite.
☐ | ~4 weeks out (1 month) | Promote everywhere & open volunteer sign-ups | Begin weekly check-in meetings to keep every action item moving.
☐ | ~2 weeks out | Confirm logistics & recruit volunteers directly | Re-confirm all rentals, donations, and entertainment (exact delivery/pickup windows).
☐ | ~2 weeks out | Confirm logistics & recruit volunteers directly | Decide on a port-a-potty and confirm where it can be placed.
☐ | ~2 weeks out | Confirm logistics & recruit volunteers directly | After people RSVP, personally ask them to take a 30-60 min volunteer slot.
☐ | ~2 weeks out | Confirm logistics & recruit volunteers directly | Finalize the day-of run of show and assign a lead to each segment.
☐ | ~2 weeks out | Confirm logistics & recruit volunteers directly | Plan welcome/name-tag tables at BOTH ends of the block.
☐ | Week of the party | Buy, prep & remind | Buy/gather: ice, coolers, drinks, cups, plates, utensils, napkins, trash bags, tape, name tags.
☐ | Week of the party | Buy, prep & remind | Print donation QR codes and 'sponsored by' signs.
☐ | Week of the party | Buy, prep & remind | Make a map/signage of where everything is, posted at the entrances.
☐ | Week of the party | Buy, prep & remind | Send a reminder with timing, BYOB/potluck note, and parking guidance.
☐ | Week of the party | Buy, prep & remind | Confirm who picks up each food donation and rental, and when.
☐ | Day before | Stage everything | Have tables, chairs, and barriers delivered (often Friday for a weekend party).
☐ | Day before | Stage everything | Move all party supplies to one staging spot (a front porch works).
☐ | Day before | Stage everything | Fill coolers / pre-chill drinks.
☐ | Day before | Stage everything | Do a final volunteer confirmation text for the setup crew.
☐ | Day before | Stage everything | Charge speakers; test the sound system and microphone.
☐ | Party day | Set up, host, and keep it safe | Place barriers and station an adult monitor at each closure point all event long.
☐ | Party day | Set up, host, and keep it safe | Set up tables, decorations, welcome/name-tag tables, kids' zone, and food area.
☐ | Party day | Set up, host, and keep it safe | Keep an emergency lane clear so fire/EMS can pass.
☐ | Party day | Set up, host, and keep it safe | Run the schedule; keep water and shade available.
☐ | Party day | Set up, host, and keep it safe | Take photos and capture a group shot.
☐ | After the party | Break down, return & say thank you | Break down chairs/tables, bag trash & recycling, sweep the street.
☐ | After the party | Break down, return & say thank you | Wash and return linens, serving gear, coolers, and borrowed items.
☐ | After the party | Break down, return & say thank you | Schedule rental pickups (often the Monday after).
☐ | After the party | Break down, return & say thank you | Write thank-you notes to every donor/business; ask the association to highlight them.
☐ | After the party | Break down, return & say thank you | Hold a short debrief: what to keep, what to change; start the 'next year' list.
☐
☐
☐
☐
☐
☐

## Budget Tracker
Budget Tracker
Template with rough Austin estimates - replace with your own numbers. Costs vary a lot with block size and how much you fundraise.
Item | Vendor / Source | Estimated Cost | Actual Cost | Funded By | Receipt? | Notes
City permit (application fee + 4%) | City of Austin | 52 |  | TBD | ☐
Tables & chairs | Rental company | 650 |  | TBD | ☐
Barriers / barricades | City loaner program or rental | 150 |  | TBD | ☐
Tent (10x10 pop-ups) | Rental or purchase | 0 |  | TBD | ☐
Port-a-potty | Rental company | 160 |  | TBD | ☐
Entertainment (band/DJ/troupe) |  | 400 |  | TBD | ☐
Yard games & rentals | Rental company | 106 |  | TBD | ☐
Food anchor (beyond potluck) | Local restaurant/caterer | 200 |  | TBD | ☐
Supplies (ice, cups, plates, etc.) | Grocery/warehouse store | 150 |  | TBD | ☐
Decorations | Craft/party store | 100 |  | TBD | ☐
Printing (flyers) | Local printer - ask to donate | 0 |  | TBD | ☐
|  |  |  | TBD | ☐
|  |  |  | TBD | ☐
|  |  |  | TBD | ☐
|  |  |  | TBD | ☐
|  |  |  | TBD | ☐
TOTALS
Summary
Total estimated
Total actual spent
In-kind / donated value
Out-of-pocket (cash)

## Donations & Sponsors
Donations & Sponsors
Track every donor. The two example rows are just illustrations - overwrite them.
Confirmed | Business / Donor | Type | What they're giving | Est. value ($) | Pickup / delivery date & time | Thank-you sent | Notes
☐ | Example: local taqueria | Goods | Queso & chips for ~50 | 0 | Party day, 3:30 pm | ☐ | Replace with your own donor
☐ | Example: neighborhood assoc. | Cash | Event sponsorship | 200 | n/a | ☐ | Ask them to feature donors in the newsletter
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
☐ | [5 empty] | ☐
Total est. donated value